## GUI APP
Nhiệm vụ
Login Photo Facebook
Login
Account Information
Avatar
Name Facebook
Live in Ho Chi Minh City
Day of birth
Friend List
Avatar Friend
Name Facebook
Avatar Friend
Name Facebook
Avatar Friend
Name Facebook
Avatar Friend
Name Facebook
Friend
Photo
Detail Photo
Image
Album Photo
Image
Friend
Photo
Login
Login

## issues
NO. | issues | description | date | resolve solution | date
1 | commit code between 2 menbers | 2 members create onther folder in project, when merge in code we had error | 26/06/2017 | solution1:delete project and create new one in githud | 27/06/2017
2 | import fra to FBSDK.framework
3
4
5
6
7
8
9
10
11
12

## tasks manager
NO. | tasks | subtasks | estimation(h) | estimation(h) | estimation(h) | assignee | start date | end date | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | create base | create stucture project | 2 | 2 | 2 | quyennt | 2017-06-27
|  | create tabbar Account information & photo | 1 | 1 | 1 | duydn | 2017-06-27 | 2017-06-27
|  | use cocoapod add FBSDK | 0.5 | 1 | 0.75 | quyennt | 2017-06-27 | 2017-06-27
|  | design class diagram | 16 | 16 | 16 | quyennt+duydn | 2017-06-28
2 | Login | Design GUI Login | 0.5 | 0.5 | 0.5 | duydn | 2017-06-27 | 2017-06-27
|  | implement Login function | 0.5 | 1 | 0.75 | quyennt | 2017-06-27 | 2017-02-27
| Account information | design GUI account information | 1 | 0.5 | 0.75 | duydn | 2017-06-27 | 2017-06-27
|  | get my information | 2 | 3 | 2.5 | duydn | 2017-06-27 | 2017-06-27
|  | get friend information | 3 | 6 | 4.5 | quyennt | 2017-06-27
|  | load more friend | 8 | 8 | 8 | quyennt+duydn | 2017-06-29
| Photo | design GUI photo | 0.5 | 0.5 | 0.5 | duydn | 2017-06-30
|  | get list image | 4 | 4 | 4 | duydn | 2017-06-30
|  | lazy loading images | 16 | 16 | 16 | quyennt+duydn | 2017-07-03
| Photo detail | Design GUI photo detail | 0.5 | 0.5 | 0.5 | duydn | 2017-07-04
|  | Zoom in/zoom out | 1 | 4 | 2.5 | duydn | 2017-07-05
|  | rotation | 3 | 4 | 3.5 | quyennt | 2017-07-05
|  |  | 59.5 | 68 | 63.75
|  |  | 7.4375 | 8.5 | 7.9688